## 018-E-DAT-00014-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 4 | Rashed Almudahka | Spec. and grade to be specified for tie rods and spacers material.
2 | Call-out | 4 | Rashed Almudahka | Channel cover, tube sheet and baffles material are different from updated EDP. JV to clarify