## 018-E-DAT-00027-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | General Comment: Remove the space between the sequence number and suffix
2 | Call-out | 2 | Rashed Almudahka | Surface area is less than what is indicated in the EDP. please clarify.
3 | Call-out | 3 | Rashed Almudahka | Central spacing is not in line with EDP requirement. please modify.
4 | Call-out | 3 | Rashed Almudahka | Shell ID shall be 56" as per EDP. please modify.
5 | Call-out | 4 | Rashed Almudahka | Note 14 to be added for floating head material spec. and grade.
6 | Call-out | 4 | Rashed Almudahka | Shell cover CA shall be 3/16" as per EDP. please indicate.
7 | Callout | 6 | Fatema Hashem | TYPO: PRESSURE