## 018-E-DAT-00030-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | General Comment: Remove the space between the sequence number and suffix
2 | Call-out | 2 | Rashed Almudahka | Surface area is less than what is indicated in the EDP. please clarify.
3 | Callout | 2 | Fatema Hashem | DATA IS INCONSISTENT WITH H&MB. REVIEW AND CORRECT
4 | Text Box | 4 | Rashed Almudahka | provide the specification and grade for the following: 1. baffles 2. support plates 3. tie rods and spacers
5 | Callout | 7 | Fatema Hashem | OBTAIN LICENSOR CONFIRMATION OF THE HEAT CURVES UPDATED FOR SINGLE STAGE MEMBRANE OPERATION