## 018-E-DAT-00031-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | CHECK WITH H&MB AND CORRECT
2 | Call-out | 2 | Rashed Almudahka | Surface area is less than what is indicated in the EDP. please clarify.
3 | Callout | 3 | Fatema Hashem | ADVISE WHY THE TUBE-SIDE DESIGN TEMPERATURE IS REDUCED FROM 500F TO 440F?
4 | Text Box | 4 | Rashed Almudahka | provide the specification and grade for the following: 1. baffles 2. support plates 3. tie rods and spacers
5 | Call-out | 4 | Rashed Almudahka | please confirm the wind velocity of 176 ft/sec.
6 | Callout | 7 | Fatema Hashem | OBTAIN LICENSOR CONFIRMATION OF THE HEAT CURVES UPDATED FOR SINGLE STAGE MEMBRANE OPERATION