## 018-E-DAT-00054-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 2 | Fatema Hashem | pressure is 96 on H&MB. Check and confirm
3 | Callout | 2 | Fatema Hashem | clarify why exchanger type was changed from BKU?
4 | Callout | 3 | Fatema Hashem | clarify the reason for reducing the tubes design temperature from 500F to 450F?