## 018-E-GAD-00017-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | MHA/HA/MAK: Confirmed
2 | Text Box | 1 | Rashed Almudahka | TYPICAL COMMENT FOR ALL EXCHANGERS: OWNER have noticed some flange thickness and details has been changed/ modified. Contractor to clarify the basis of these changes.