## 018-E-GAD-00039-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Rashed Almudahka | As per EPC data sheet, baffles material spec. is SA516 GR60N. please clarify
2 | Call-out | 1 | Rashed Almudahka | As per unit P&ID, tube side inlet and outlet is 6" size. please clarify
3 | Text Box | 1 | Rashed Almudahka | Comments on 018E2012 GADs are applicable to all drawings in this transmittal.
4 | Call-out | 1 | Rashed Almudahka | FEED data sheet showing that stress relieving is required for tube side. Please clarify.
5 | Call-out | 1 | Rashed Almudahka | Provide grade and spec. of tie rods and spacers material
6 | Call-out | 1 | Rashed Almudahka | provide the basis of choosing B7 nut & bolts over B16
7 | Text Box | 1 | rob.urban | The Owner does not have the means to verify the calculations undertaken by the Contractor and can only verify certain data included within the report from available documentation. It is the Contractor’s responsibility to ensure correctness and accuracy of the data in line with the terms of the Contract.