## 018-E-GAD-00040-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 5
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Text Box | 1 | Mahdi Ali | ALL THE TEXT IN THIS DRAWING SHALL SEARCHABLE. TEXT FONTS AND STYLES SHALL BE AS PER BMPS-A8
4 | Call-out | 1 | Rashed Almudahka | baffles material shall be normalized as per data sheet. please clarify.
5 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
6 | Call-out | 1 | Rashed Almudahka | P&ID shows tube side inlet and outlet as 6". please clarify
7 | Call-out | 1 | Rashed Almudahka | provide the basis of choosing B7 bolts & nuts over B16
8 | Call-out | 1 | Rashed Almudahka | provide the spec. and grade for material of tie rods and spacers
9 | Text Box | 1 | rob.urban | The Owner does not have the means to verify the calculations undertaken by the Contractor and can only verify certain data included within the report from available documentation. It is the Contractor’s responsibility to ensure correctness and accuracy of the data in line with the terms of the Contract.