## 018-G-DAT-00007-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 1 | Mahdi Ali | REMOVE SPACE BETWEEN TAG NUMBER AND SUFFIX
3 | Text Box | 1 | rob.urban | Comments to be discussed
4 | Text Box | 5 | Ahmed Bucheeri | YES
5 | Text Box | 5 | Ahmed Bucheeri | YES
6 | Text Box | 5 | Isamu | Please comply with FEED DS requirement for witnessed inspection and test. Changing to observed is rejected without Owner prior approval on selected test and selected pump on case by case basis. There is no "Observe" level of inspection in the ITB (BMPS-G-50309) and "witness" must be retained on the data sheet in line with the definition of the ITP. Also Refer to BMPS-B11 / BMPS-G1 / API 610 parag 3.64 and 3.38 for definitions of witness.
7 | Callout | 7 | Fatema Hashem | elevation of 018C0003 is 43ft according to HVGO PA pumps datasheet. Review and correct