## 018-G-DAT-00009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 1 | Mahdi Ali | REMOVE SPACE BETWEEN TAG NUMBER AND SUFFIX
3 | Text Box | 1 | rob.urban | Comments to be discussed
4 | Callout | 2 | Fatema Hashem | Clarify the reason for changing the wash oil vapour pressure from 0.765 to 0.83?
5 | Call-out | 3 | Ahmed Bucheeri | Class S6 in EDP and FEED sheets, to clarify with licenser
6 | Text Box | 4 | Isamu | FEED DS asked for plan 11 to flush the primary seal. Please justify why it is deleted, consider applying plan 21 in conjunction with pump/seal maker recommendations.
7 | Text Box | 4 | Isamu | FEED DS opted for SS piping, flanges and socket welding and these shall prevail per Owner decision. Please comply and correct even though tubing is mentioned in BMPS-G9
8 | Text Box | 4 | AliRedha Malalla | -19
9 | Text Box | 5 | Isamu | Please comply with FEED DS requirement for witnessed inspection and test. Changing to observed is rejected without Owner prior approval on selected test and selected pump on case by case basis. There is no "Observe" level of inspection in the ITB (BMPS-G-50309) and "witness" must be retained on the data sheet in line with the definition of the ITP. Also Refer to BMPS-B11 / BMPS-G1 / API 610 parag 3.64 and 3.38 for definitions of witness.
10 | Text Box | 5 | Ahmed Bucheeri | YES
11 | Text Box | 5 | Ahmed Bucheeri | YES
12 | Callout | 7 | Fatema Hashem | elevation of 018C0003 is 44.3ft according to LVGO pumps datasheet. Review and correct
13 | Text Box | 7 | AliRedha Malalla | 19. PUMP & M/SEAL OEM SHALL PROVIDE MEASURED STUFFING BOX PRESSURE.