## 018-G-DAT-00015-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit. - The correct equipment tag nos. shall be used. Refer to the latest Equipment List (Item Index).
2 | Text Box | 1 | Ravi Kumar | OPEN COMMENTS OF REV A DATASHEET TO BE CLOSED
3 | Cloud+ | 1 | MAK | NO. 1 RESIDUE HYDROCRACKING UNIT
4 | Callout | 2 | Mahdi Ali | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
5 | Callout | 2 | Fatema Hashem | PLEASE NOTE THAT DIESEL FLUSHING OIL RETURN MAY BE ROUTED TO THESE PUMPS AND HENCE INCLUDE DIESEL PROPERTIES TOO WITH APPROPRIATE NOTE
6 | Callout | 7 | Fatema Hashem | REFER TO JV RESPONSE TO COMMENTS MADE ON REV A WITH REGARDS TO NOTE 11:"note is referring to the flushing operation of flushing the heat exchangers with cold MVGO. Value of viscosity needs to be updated to 17.81cP according to the air cooler E0026 outlet viscosity". 1. PLEASE NOTE THIS IS A PUMP AND NOT A HEAT EXCHANGER, PLEASE MODIFY THE NOTE. 2. PLEASE NOTE THAT E0026 IS NOT AN AIR COOLER AND THAT IT IS NOT CONNECTED WITH THIS PUMP. I BELIEVE TTSJV ARE REFERRING TO THE VISCOSITY ON THE OUTLET OF E0023. 3. PLEASE CLARIFY WHERE THE VISCOSITY HAS BEEN UPDATED TO 17.81cP.
7 | Callout | 7 | Mahdi Ali | EQUIPMENT TAG SHALL CONTAIN SPACE