## 018-G-DAT-00028-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | General comment to all pumps: pressures shown on datasheets are inconsistent with P&IDs. review and correct where applicable.
2 | Text Box | 2 | Isamu | Please use dot (.) instead of comma (,) on all cells to fill to avoid confusion
3 | Text Box | 3 | Isamu | VG 46 is not suitable for integrally geared pump but ATF-20. Delete and leave it to Vendor.
4 | Text Box | 4 | Isamu | All seal flush and seal barrier liquid lines shall be SS piping as per FEED data sheet. Contractor is not at liberty to select softer option in case of conflict between various project documents. Correct and apply to all pumps