## 018-G-DAT-00029-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Text Box | 1 | Ravi Kumar | OPEN COMMENT IN RESOLUTION SHEET OF REV A DATASHEET TO BE CLOSED
3 | Call-out | 2 | Ali Hasan | In reference with Note 3, the pump and pump’s internals shall be designed to withstand the maximum draining oil temperature limited by the RPSO underground piping. Please include the pump design temperature in the data sheet or in Note 3.
4 | Callout | 2 | Mahdi Ali | INDICATE UNIT NO. AND THE FULL DESCRIPTION
5 | Call-out | 2 | Ebrahim | Indicate method of starting the motor. Normally, Direct-On-Line (DOL)
6 | Call-out | 3 | Ali Hasan | The rational for 175 deg is not clear. Please review the discharge piping design temperature, and consider increasing the temperature to the maximum fluid in the sump (450 deg F in Note 3) or as limited by the CS piping.
7 | Call-out | 4 | Ali Hasan | Dual-pressurized seal (plan 53B) has been specified for this pump and the other pumps in this transmittal (018P0030A/B and 018P0031A/B): 1.Please confirm with the pump vendor and the mechanical seal supplier that dual-pressurized seal can be used for these pumps considering that the pumps are intermittent service, vertical (submerged) and multistage type. 2.Please ensure consistency/standardization in the mechanical seal selection with other pumps of similar in ROC, MOC and SOC.
8 | Text Box | 6 | David.Jimenez | h
9 | Text Box | 8 | Ali Hasan | The time for emptying out the sump to be included in the notes. Please add a note stating “The pump is designed to empty the sump in xxx minutes”.
10 | Callout | 8 | Mahdi Ali | ADD DATASHEET NUMBER IF AVAILABLE
11 | Call-out | 8 | Hasan Al Noaimi | full set motor and pump