## 018-G-DAT-00030-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | EQUIPMENT NUMBERS SHALL NOT CONTAIN SPACES
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Text Box | 1 | Rashed Almudahka | TYPICAL COMMENTs are applicable for all centrifugal pumps submitted through this transmittal.
4 | Callout | 3 | Isamu | Feed asked for VS4. Please justify
5 | Call-out | 3 | Rashed Almudahka | TYPICAL COMMENT coupling to be in compliance with API610 as per FEED. please clarify.
6 | Text Box | 4 | Isamu | Tubing is not acceptable. Please change to SS pipings. Contractor is not at liberty to select softer option in case of conflict between project documents. FYI, Pressurized plan 53B is a flushing plan and it has to be filled regularly.
7 | Text Box | 5 | Rashed Almudahka | TYPICAL COMMENT Provide the basis of changing the inspection/ test requirement
8 | Text Box | 6 | David.Jimenez | drawing no.?
9 | Call-out | 7 | Rashed Almudahka | TYPICAL COMMENT Provide the basis of removing the remark from FEED data sheet.
10 | Call-out | 7 | Rashed Almudahka | TYPICAL COMMENT table 11 is referring to (power rating for motor drivers) in API610. please clarify.