## 018-G-DAT-00031-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | EQUIPMENT NUMBERS SHALL NOT CONTAIN SPACES
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Callout | 3 | Isamu | Feed asked for VS4. Please justify
4 | Text Box | 4 | Isamu | Tubing is not acceptable. Please change to SS pipings. Contractor is not at liberty to select softer option in case of conflict between project documents. FYI, Pressurized plan 53B is a flushing plan and it has to be filled regularly.
5 | Text Box | 6 | David.Jimenez | drawing no?