## 018-G-DAT-00036-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 2 | Isamu | Please use dot (.) instead of comma (,) on all cells to fill to avoid confusion
2 | Text Box | 3 | Isamu | RF can not be used with such high rating. Change to RJT
3 | Text Box | 3 | Isamu | VG 46 is not suitable for integrally geared pump but ATF-20. Delete and leave it to Vendor.
4 | Text Box | 4 | Isamu | Plan 13 is suitable for volatile / saturated liquid of very low specific gravity. Should be left empty for the Vendor to recommend and decide
5 | Text Box | 7 | Isamu | Check and correct. How vertical motor TEFC can be oil misted ?
6 | Callout | 7 | Fatema Hashem | correct to "should"