## 018-S-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Casella di testo | 2 | gmazzocchitti | 018U1001/2001
2 | Casella di testo | 3 | gmazzocchitti | (to no.1 Hydrogen Recovery Unit - 1HRU)
3 | Casella di testo | 3 | gmazzocchitti | 018U1001/2001
4 | Casella di testo | 3 | gmazzocchitti | 4.7 Steam Out conditions
5 | Casella di testo | 4 | gmazzocchitti | 018U1001
6 | Casella di testo | 4 | gmazzocchitti | 018U1001/2001
7 | Casella di testo | 4 | gmazzocchitti | 018U2001
8 | Casella di testo | 4 | gmazzocchitti | contact EPC Contractor.
9 | Text Box | 4 | fbarbieri1 | Refer to project specification BMPS-A2
10 | Casella di testo | 5 | gmazzocchitti | (018U1001/2001)
11 | Casella di testo | 5 | gmazzocchitti | 018U1001/2001
12 | Text Box | 5 | Fbarbieri1 | 96.5%
13 | Casella di testo | 5 | gmazzocchitti | a single
14 | Call-out | 5 | Rashed Almudahka | As per PFD, expected temperature is 201F. JV to add the same with a note for vendor to confirm
15 | Casella di testo | 5 | gmazzocchitti | at the inlet
16 | Casella di testo | 5 | gmazzocchitti | coming
17 | Text Box | 5 | fbarbieri1 | Deleted
18 | Callout | 5 | Fatema Hashem | INCLUDE THE NOTE FROM CLG DATASHEET IN THE DESIGN BASIS: "VENDOR TO PROVIDE SYSTEM CONFIGURATION INCLUDING ITEMS OUTSIDE VENDOR SCOPE THAT INTERFACE WITH THE MEMBRANE UNIT".
19 | Call-out | 5 | Rashed Almudahka | MODIFY at the membrane unit inlet
20 | Casella di testo | 5 | gmazzocchitti | non-permeate
21 | Casella di testo | 5 | gmazzocchitti | The
22 | Casella di testo | 5 | gmazzocchitti | to 1HRU.
23 | Casella di testo | 6 | gmazzocchitti | 018U1001/2001
24 | Call-out | 6 | Rashed Almudahka | as per H&MB, temperature is 174F. please clarify
25 | Text Box | 6 | Fbarbieri1 | Composition to be supplied by vendor. Pressure, Psi(g) 483 Temperature, °F 165 (Vendor to confirm)
26 | Callout | 6 | Robert.Kawitzki | Length
27 | Text Box | 6 | fbarbieri1 | Membrane Unit will be installed within the following plot area: - Lenght: 6500 mm To be confirmed by Vendor; - Width: 14000 mm To be confirmed by Vendor; - Height: To be defined by Vendor; Vendor shall include in technical proposal preliminary general arrangement drawing of the membrane unit, with main dimensions and the required maintenance areas.
28 | Text Box | 6 | esereno | Refer to BMPS-A1 (Basic Engineering Design Data)
29 | Casella di testo | 7 | gmazzocchitti | 018U1001/2001
30 | Callout | 7 | Fatema Hashem | EVALUATE THE CASE OF HP WASH WATER PUMP FAILURE AND ITS EFFECT ON THE COMPOSITION OF THE FEED TO MEMBRANE
31 | Callout | 7 | rob.urban | Not required
32 | Text Box | 7 | Fbarbieri1 | Vendor to provide permeate/non permeate gas flow and composition
33 | Casella di testo | 8 | gmazzocchitti | 018U1001/2001
34 | Text Box | 8 | Fbarbieri1 | 2.9.12 Cause&Effect Diagram and Interlock Description.
35 | Casella di testo | 9 | gmazzocchitti | 018U1001/2001
36 | Text Box | 9 | fbarbieri1 | Deliverable document list and document delivery schedule are detailed in 000-S-SOW-60006-001.
37 | Casella di testo | 9 | gmazzocchitti | EPC Contractor
38 | Text Box | 9 | fbarbieri1 | Refer to para.3.1 of 000-S-GRD-60006-001, "Particular Technical Specification for Membrane Unit"
39 | Casella di testo | 10 | gmazzocchitti | /EPC Contractor.
40 | Casella di testo | 10 | gmazzocchitti | 018U1001/2001
41 | Call-out | 10 | Jawad Alawi | Delete
42 | Text Box | 10 | fbarbieri1 | Deleted
43 | Casella di testo | 10 | gmazzocchitti | Equipment is under Hydrogen service and Low severity Sour service. Materials to comply with BMPS-A26. Non CS components, materials to comply with NACE MR0103.
44 | Text Box | 10 | fbarbieri1 | Refer to para.3.1 of 000-S-GRD-60006-001, "Particular Technical Specification for Membrane Unit"
45 | Text Box | 10 | AliRedha Malalla | Vendor to specify any special location and size requirement for maintenance.
46 | Text Box | 11 | FBarbieri1 | 82
47 | Text Box | 11 | Fbarbieri1 | 1556 (Note 1)
48 | Text Box | 11 | Fbarbieri1 | 4.7 Steam Out Conditions
49 | Text Box | 11 | Fbarbieri1 | 475 (Note 1)
50 | Text Box | 11 | Fbarbieri1 | 605
51 | Text Box | 11 | Fbarbieri1 | Permeate
52 | Casella di testo | 11 | gmazzocchitti | 018U1001/2001
53 | Text Box | 11 | FBarbieri1 | 1
54 | Text Box | 11 | Fbarbieri1 | 475 (Note 1)
55 | Text Box | 11 | Fbarbieri1 | 475 (Note 1)
56 | Text Box | 11 | Fbarbieri1 | 6"/300RF/C36NH
57 | Text Box | 11 | Fbarbieri1 | 8"/1500RF/F30NH 8"/900RF/E1NH
58 | Call-out | 11 | Rashed Almudahka | as per BMPS-L2, piping classes F30NH & E1NH maximum temperature is 450F. please clarify
59 | Text Box | 11 | AliRedha Malalla | Detailed maintenance requirements for both routine and non-routine to be included in the maintenance document report. It shall include all safety requirements.
60 | Casella di testo | 11 | gmazzocchitti | EPC Contractor
61 | Text Box | 11 | Fbarbieri1 | Equipment and piping subject to the steam-out conditions shall be designed for the Steam Out conditions stated at BMPS-A3
62 | Text Box | 11 | Fbarbieri1 | Note 1: Design conditions to be confirmed by vendor and/or EPC contractor
63 | Text Box | 11 | FBarbieri1 | Piping Line Classes, BMPS-L2
64 | Text Box | 11 | FBarbieri1 | Piping shall be manufactured and tested according to BMPS-B3
65 | Text Box | 11 | Fbarbieri1 | Size/Rating/Piping Class
66 | Text Box | 11 | Fbarbieri1 | Sound pressure levels generated by Membrane Unit shall be within the limits specified in BMPS-A21.
67 | Casella di testo | 12 | gmazzocchitti | 018U1001/2001
68 | Text Box | 12 | fbarbieri1 | All the instruments and relevant installation material shall comply with the requirements of BMPS-J6, Instruments for Package Units
69 | Text Box | 12 | fbarbieri1 | Electrical design for package unit shall be in compliance with BMPS-P3 `Electrical Requirements for Package Units'.
70 | Casella di testo | 12 | gmazzocchitti | EPC Contractor
71 | Text Box | 12 | fbarbieri1 | Hazardous Area Classification is Zone 2 IIC T3 HOLD.
72 | Text Box | 12 | Omran A | IFAT/FAT
73 | Text Box | 12 | fbarbieri1 | Membrane Unit control shall be performed through DCS
74 | Text Box | 12 | Omran A | Note: for item 6.5, it's valid If the licensor approves that the main control shall be from DCS. Also, the vendor shall provide the control narrative for deploying control philosophy in DCS.
75 | Text Box | 12 | jjimenez | Specification BMPS-A1.
76 | Text Box | 12 | FBarbieri1 | the environmental condition reported in Basic Design
77 | Text Box | 13 | fbarbieri1 | , Foundation Fieldbus, FISCO certified.
78 | Casella di testo | 13 | gmazzocchitti | 018U1001/2001
79 | Casella di testo | 13 | gmazzocchitti | according to BMPS- A1 units.
80 | Text Box | 13 | Omran A | and shut-down sequences in the control system HMI (DCS, SCADA or any)
81 | Text Box | 13 | fbarbieri1 | Deliverable document list and document delivery schedule are detailed in 000-S-SOW-60006-001.
82 | Text Box | 13 | Omran A | Vendor shall configure an animated Graphic page for the start-up
83 | Callout | 13 | rob.urban | Vendor shall incorporate all instrument or control system signals from the Residue Hydrocracker which have effect on or interact with operation of the Membrane unit (Cutbacks, Shutdown signals etc.)
84 | Casella di testo | 14 | gmazzocchitti | 018U1001/2001
85 | Casella di testo | 14 | gmazzocchitti | EPC Contractor
86 | Casella di testo | 14 | gmazzocchitti | EPC Contractor
87 | Text Box | 14 | fbarbieri1 | For Quality assurance and Inspection requirements, refer to 000-S-GRD-60006-001, "Particular Specification for Membrane Unit".
88 | Call-out | 14 | Jawad Alawi | Has this document issued? Does it cover inspection plan and manufacturing procedures, Testing?
89 | Text Box | 15 | Fbarbieri1 | (Note1)
90 | Casella di testo | 15 | gmazzocchitti | 018U1001/2001
91 | Callout | 15 | Fatema Hashem | ADD NOTE: VENDOR TO PROVIDE TYPE AND QUANTITY OF CONTAMINANTS (IF ANY) THAT COULD BE DANGEROUS FOR MEMBRANE AND THEIR POTENTIAL IMPACT ON PROCESS PERFORMANCE.
92 | Callout | 15 | Fatema Hashem | ADVISE THE MAXIMUM CONTENT OF MDEA IN THE MEMBRANE FEED?
93 | Callout | 15 | Fatema Hashem | IN BURGAS, A NOTE IS ADDED FOR MAXIMUM CHLORIDE CONTENT IN THE MEMBRANE FEED. ADVISE THE RATIONALE FOR NOT SPECIFYING CHLORIDE CONTENT IN 1RHCU?
94 | Text Box | 15 | Fbarbieri1 | Membrane
95 | Text Box | 15 | Fbarbieri1 | Note 1: This stream is the sum of the Feed to Single Stage plus Membrane by-passed gas.