## 021-A-CAL-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | This document is not a Calculations document. Change this to TSP.
2 | Cloud+ | 1 | MAK | NO. 3 HYDRODESULPHURIZATION UNIT
3 | Call-out | 3 | Rashed Almudahka | For more clarity, avoid using two definitions for the same meaning.
4 | Text Box | 7 | Bader Abdulrahman | Redundant term "According to BMPS-M6...etc is" sufficient
5 | Callout | 8 | mohamed.waleed | Have we got this agreement recorded in any FEED Basis of design document or MOMs, please share.
6 | Text Box | 8 | mohamed.waleed | Please identify in attachment-1 wherein we are facing this scenario
7 | Text Box | 13 | Rashed Almudahka | Ensure hazardous area classification is taken into consideration as well.
8 | Text Box | 13 | MAK | Add a reference to Bapco Doc. No. on every attachment page, e.g. Attachment 1 of 021-A-TSP-00001-001.
9 | Cloud+ | 14 | MAK | Delete S
10 | Cloud+ | 14 | MAK | Delete S
11 | Call-out | 15 | MAK | Delete S