## 021-A-EQL-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 4 | Ali Kadhem | Design Temperature 285F Operating Temperature 260F
2 | Call-out | 5 | Ali Kadhem | As per IBD P&ID, the Ejector Receiver 021V0013 design pressure is 225psig.
3 | Call-out | 3 | Mahdi Ali | MAKE SURE THAT THE DRAWING NUMBER IS IN ONE LINE. THIS IS IMPORTANT FOR BAPCO FOR BUILDING RELATIONSHIP BETWEEN TAGS AND REFERENCES.
4 | Call-out | 1 | MAK | 021 - NO. 3 HYDRODESULPHURIZATION UNIT - 3HDU
5 | Text Box | 1 | MAK | General Comment: Use the latest document template that is part of the Homogenisation Procedure. Use A3 cover page for A3 size documents.
6 | Call-out | 3 | MAK | Delete ELECTRIC in all FINFAN description.
7 | Call-out | 3 | MAK | Desuperheater material class is "L"
8 | Call-out | 3 | MAK | For easy reading, It's recommended to sort out the table by Material Class and then by Tag Nos.
9 | Call-out | 4 | MAK | Delete ELECTRIC in all FINFAN description.
10 | Call-out | 5 | MAK | Condenser material class is "E"
11 | Call-out | 6 | MAK | Add 3HDU before FEED and delete (Tank Farm)
12 | Call-out | 6 | MAK | The tag numbers shall be changed to: 934DS2100A 934DS2100B 934M2100C 934P2100A 934P2100B 934P2100C 934T2100A 934T2100B
13 | Call-out | 6 | MAK | Change to "G"
14 | Call-out | 6 | MAK | Add 3HDU FEED PUMP before TURBINE and change the tag nos. accordingly.
15 | Call-out | 6 | MAK | Change the tag nos.
16 | Call-out | 6 | MAK | Delete S
17 | Call-out | 6 | MAK | Delete S
18 | Call-out | 6 | MAK | Fill in Material Class
19 | Call-out | 6 | MAK | Change to "K"
20 | Text Box | 1 | rob.urban | LIST NEEDS TO BE RE-ARRANGED BY EQUIPMENT TYPE AND TAG NUMBER IN LOGICAL SEQUENCE