## 021-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | Please refer to Technical Query T1128 regarding the thickness of columns internals and ensure complience with the owner response: For 3HDU Column Internals, Bidder shall select the more stringent between UOP spec 3-18-2/ BMPS-C10/ BMPSC11 to determine the thicknesses.
2 | Call-out | 2 | Ali Kadhem | It is noted that in the EDP/FEED datasheets the design condition was Full vacuum at 300F. Please provide basis for changing the temperature from 300F to 735F
3 | Call-out | 2 | Ali Kadhem | It is noted that in the maximum hyfrogen partial pressure has been revised from 46 psia to 148 psia. Please provide basis for this change.
4 | Call-out | 2 | Rashed Almudahka | Parts thickness to be indicated where applicable.
5 | Text Box | 4 | Ali Kadhem | Please refer to the comments provided in email: "3HDU - Pre EPC - Comments on some datasheets", dated 3 April 2018: It is noted in FEED datasheet that many dimensions w.r.t. tray spacing are not rounded off to the nearest mm while converting from UOP datasheet; there is a variation of about 5mm in some rounding off. EPCContractor should refer to UOP datasheet for the base dimensions and round off to nearest mm while developing the EPC datasheet.
6 | Call-out | 5 | Rashed Almudahka | Ensure the modified man-way sizes are reflected in the P&ID