## 021-C-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | Please refer to Technical Query T1128 regarding the thickness of columns internals and ensure complience with the owner response: For 3HDU Column Internals, Bidder shall select the more stringent between UOP spec 3-18-2/ BMPS-C10/ BMPSC11 to determine the thicknesses.
2 | Call-out | 2 | Rashed Almudahka | Parts thickness to be incorporated where applicable.
3 | Text Box | 4 | Ali Kadhem | Please refer to the comments provided in email: "3HDU - Pre EPC - Comments on some datasheets", dated 3 April 2018: As per the sketch in the datasheet, the gas entry is shown above the LIT top tap. However, based on the dimensions, the gas entry will be below the top level tap. This issue was raised to UOP during FEED and UOP had confirmed that the dimesions are correct. Bapco has a concern with this arrangement i.e. gas entry being below 100% liquid level reading. Bapco preference is to keep the gas entry point above the upper liquid level tap. UOP's further clarification for the rational of the current arrangement and to advise if they foresee any concern with Bapco's preferred arrangement.
4 | Call-out | 5 | Rashed Almudahka | Note19 shall be applicable for all #3HDU vessels/ columns as per TQ1128