## 021-C-DAT-00003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | Please refer to Technical Query T1128 regarding the thickness of columns internals and ensure complience with the owner response: For 3HDU Column Internals, Bidder shall select the more stringent between UOP spec 3-18-2/ BMPS-C10/ BMPSC11 to determine the thicknesses.
2 | Call-out | 2 | Ali Kadhem | It is noted that the temperature and pressure in this datasheet are different than the H&MB. Please confirm.
3 | Call-out | 2 | Ali Kadhem | Please refer to Technical Query T1739 regarding external design condition. It is noted that in this datasheet the external design temperature is specified as 660F. Please review.
4 | Call-out | 4 | Rashed Almudahka | Height is differs from FEED. please clarify
5 | Call-out | 5 | Rashed Almudahka | PG connection shall be part from this bridle. please clarify
6 | Call-out | 5 | Ali Kadhem | Please refer to the P&ID and EDP Datasheet, the Nozzle (N5) size is 6". Please revise/confirm.
7 | Call-out | 6 | Ali Kadhem | It is noted that the temperature and pressure in this datasheet are different than the H&MB. Please confirm.