## 021-C-DAT-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | Please refer to Technical Query T463 regarding the residence time between HLL and LLL, LLL and LLLL and ensure complience with the owner response.
2 | Call-out | 2 | Rashed Almudahka | Flanges grade has been changed from LF2 as per FEED to LF1. please clarify.
3 | Call-out | 3 | Rashed Almudahka | Wind speed is not as per BMPS-A1. please clarify.
4 | Call-out | 4 | Rashed Almudahka | Clarify the reasons behind modifying the LLL height.
5 | Text Box | 5 | Ali Kadhem | Please refer to the comments provided in email: "3HDU - Pre EPC - Comments on some datasheets", dated 3 April 2018: Basis UOP KOD V2109 datasheet, the intention is to maintain a NLL 13" above T/L apparently to maintain a seal with d/s CLPS. On this basis a low level alram has been provided. Accordingly delete Note 17 "Vessel is normally empty" on the FEED datasheet.
6 | Call-out | 5 | Rashed Almudahka | Vent nozzle size has been increased. please clarify.