## 021-C-DAT-00010-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Rashed Almudahka | Refer to OWNER comment on the notes sheet with regards to modifying the vessel dimensions and capacity.
2 | Call-out | 2 | Ahmed Bucheeri | GR LF2 as per feed sheet
3 | Call-out | 2 | Rashed Almudahka | Change the wrong asset number in the bottom label in all sheets to meet the correct asset number i.e. 021V0023
4 | Call-out | 3 | Rashed Almudahka | As per BMPS-N1, P.P. is not required for asset operating temperature, please clarify
5 | Call-out | 3 | Rashed Almudahka | It is noted that 20minutes was provided between HHLL to HLL in FEED data sheet, but, it is changed in this data sheet to 20minutes from HHLL to LLL. However, 1RHCU Flare KOD 018V0060 FEED data sheet and the latest EPC data sheet issued by TTSJV, 20 minutes was provided between HHLL and HLL, which is also consistent with BMPS-A19. Therefore, TTSJV is requested to follow BMPS-A19 and maintain the FEED basis of 20 minutes between HHLL and HLL.
6 | Call-out | 4 | Rashed Almudahka | Refer to OWNER comment on the notes sheet with regards to modifying the vessel dimensions and capacity.