## 021-C-DAT-00012-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Rashed Almudahka | note no. 49 which is referred to for reactor dimensions is deleted. please clarify.
2 | Call-out | 2 | Ahmed Bucheeri | As per UOP material list in drawing No.992381-304-01-A1 grade of internal nuts is 8MA "316SS". Using of GR 8CA to be confirmed with licensor
3 | Call-out | 2 | Rashed Almudahka | note no. 48 which is referred to shell and head materials is deleted. please clarify.
4 | Call-out | 2 | Ahmed Bucheeri | To clarify the "CSR Sector" and why the shell at the other sector is not made from SA 336 GR F22V
5 | Call-out | 3 | Rashed Almudahka | Seismic zone to be marked as "0"
6 | Call-out | 3 | Rashed Almudahka | add a note to cover that skirt fireproofing shall be in compliance with BMPS-M6
7 | Text Box | 4 | Ali Kadhem | 3
8 | Text Box | 4 | Ali Kadhem | 3
9 | Text Box | 4 | Ali Kadhem | 3
10 | Call-out | 4 | Rashed Almudahka | all nozzle facing shall be in accordance to BMPS-L2
11 | Call-out | 4 | Ali Kadhem | With reference to UOP Drawing 992381-304-01-A1. Please check and revise.
12 | Text Box | 4 | Ali Kadhem | 2
13 | Text Box | 4 | Ali Kadhem | 2
14 | Call-out | 4 | Rashed Almudahka | note no. 33 which is referred to some nozzle sizes is deleted. please clarify.
15 | Call-out | 5 | Rashed Almudahka | Extra line under the data sheet layout to be deleted
16 | Call-out | 5 | Rashed Almudahka | asset number to be updated.
17 | Call-out | 6 | Ali Kadhem | 021C0001R
18 | Call-out | 7 | Ali Kadhem | 021C0001R
19 | Call-out | 15 | Ali Kadhem | Design
20 | Call-out | 15 | Ali Kadhem | Sheets 16 to 32:
21 | Text Box | 16 | gmariano | FOR INTERNALS CORROSION ALLOWANCE SEE NOTE (7) OF MAIN DOCUMENT.
22 | Text Box | 16 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 16 of 32
23 | Text Box | 16 | asantilli | 021C0001R
24 | Text Box | 17 | asantilli | 021C0001R
25 | Text Box | 17 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 17 of 32
26 | Text Box | 18 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 18 of 32
27 | Text Box | 18 | asantilli | 021C0001R
28 | Text Box | 19 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 19 of 32
29 | Text Box | 19 | asantilli | 021C0001R
30 | Text Box | 20 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 20 of 32
31 | Text Box | 20 | asantilli | 021C0001R
32 | Text Box | 21 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 21 of 32
33 | Text Box | 21 | asantilli | 021C0001R
34 | Text Box | 22 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 22 of 32
35 | Text Box | 22 | asantilli | 021C0001R
36 | Text Box | 23 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 23 of 32
37 | Text Box | 23 | asantilli | 021C0001R
38 | Text Box | 24 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 24 of 32
39 | Text Box | 24 | asantilli | 021C0001R
40 | Text Box | 25 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 25 of 32
41 | Text Box | 25 | asantilli | 021C0001R
42 | Text Box | 26 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 26 of 32
43 | Text Box | 26 | asantilli | 021C0001R
44 | Text Box | 27 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 27 of 32
45 | Text Box | 27 | asantilli | 021C0001R
46 | Text Box | 28 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 28 of 32
47 | Text Box | 28 | asantilli | 021C0001R
48 | Text Box | 29 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 29 of 32
49 | Text Box | 29 | asantilli | 021C0001R
50 | Text Box | 30 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 30 of 32
51 | Text Box | 30 | asantilli | 021C0001R
52 | Text Box | 31 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 31 of 32
53 | Text Box | 31 | asantilli | 021C0001R
54 | Text Box | 32 | gmariano | Doc.N. 021-C-DAT-00012-001 Rev. 0 Sh. 32 of 32
55 | Text Box | 32 | asantilli | 021C0001R