## 021-C-DAT-00016-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ahmed Bucheeri | GR LF2 as per feed sheet
2 | Call-out | 2 | Rashed Almudahka | Note no.11 is not in the notes sheet. please clarify
3 | Call-out | 2 | Rashed Almudahka | Note no.12 is not in the notes sheet. please clarify
4 | Call-out | 2 | Rashed Almudahka | Note no.14 is not in the notes sheet. please clarify
5 | Call-out | 3 | Rashed Almudahka | As per BMPS-N1, P.P. not required for this vessel operating temperature
6 | Call-out | 3 | Rashed Almudahka | design temperature is already exceeding 500F. please clarify.
7 | Text Box | 3 | Rashed Almudahka | Notes no. 12 to 15 are not included in the notes list. please clarify
8 | Text Box | 3 | Ali Kadhem | This page including the specifications and notes seem to be for the datasheet of Steam Blowdown Drum 021V0004 (Page 3 of 5, Rev.A of Issue For Inquiry). The specifications and notes in the FEED datasheet of 021V0020 need to be covered and verified in this datasheet. Please update and revise.
9 | Text Box | 3 | Ahmed Bucheeri | YES
10 | Text Box | 3 | Ahmed Bucheeri | YES
11 | Text Box | 5 | Rashed Almudahka | Referenced notes in the nozzle schedule are irrelevant except the note for manways.
12 | Call-out | 5 | Rashed Almudahka | service for N7 to be auxiliary pump out. please modify