## 021-C-DAT-00024-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Ali Kadhem | As per EDP datasheet of 021V0007 (992381-301 Sheet 19), S.G. is 0.968. Please check and confirm/revise.
2 | Call-out | 4 | Rashed Almudahka | please confirm N5, for pressure relief, location.
3 | Call-out | 4 | Rashed Almudahka | Provide the basis of changing the vessel head type from FLAT to elliptical head.
4 | Call-out | 4 | Rashed Almudahka | Vortex breaker symbol to be shown in the sketch.