## 021-C-DAT-00026-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Rashed Almudahka | TYPICLA COMMENT TO ALL DATA SHEETS Latest ASME edition to be followed.
2 | Call-out | 2 | Rashed Almudahka | Add a note to cover design temperature increment as per BMPS-A3 clause 7.2. and as per note.6 of FEED data sheet
3 | Call-out | 2 | Rashed Almudahka | design temperature is referred to note.5 which is deleted. please clarify
4 | Call-out | 2 | Rashed Almudahka | Maximum design temperature is lower than internal design temperature. please clarify
5 | Call-out | 3 | Rashed Almudahka | As per operating temperature and BMPS-N1, insulation thickness shall be 50mm. please modify.
6 | Text Box | 5 | Ali Kadhem | PALL TRINITY MICRO CORP has significant experience in supplying coalescers/coalescers media, and Sepra-Chem is the Licensor (UOP) recommended supplier. PALL TRINITY MICRO CORP and Sepra-Chem are in the BMP Approved Vendors List. Therefore, TTSJV shall ensure that both PALL TRINITY MICRO CORP and Sepra-Chem are on the vendors list that will receive the MR of both 3HDU Feed Coalescer 021V0001 and Diesel Product Coalescer 021V0012.