## 021-C-DAT-00027-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Ali Kadhem | It is noted that the Pre-filters – 1 Operating and 1 Spare have been removed from the configuration that shall be provided by the coalescer vendor in the EPC datasheet in comparison with FEED and EDP datasheets for Diesel Product Coalescer 021V0012. Additionally, as also stated in the IBD issue of the 3HDU P&ID (021-PID-00026-001) note no.5 “Pre-filters in coalescer vendor scope of work. Filter type is preliminary, to be indicated by coalesce vendor.” , therefore, the Pre-filters – 1 Operating and 1 Spare shall be on the coalescer vendor scope of work and this note to be retained also in the EPC datasheet of 021V0012.
2 | Call-out | 3 | Rashed Almudahka | Wind velocity shall be 176ft/sec as per BMPS-A1. please incorporate.
3 | Call-out | 3 | Rashed Almudahka | As per operating temperature and BMPS-N1, insulation thickness shall be 60mm. please modify.
4 | Call-out | 4 | Rashed Almudahka | N6 & N9 are combined in equipment P&ID. Ensure consistency between PDS & P&ID.
5 | Text Box | 5 | Ali Kadhem | PALL TRINITY MICRO CORP has significant experience in supplying coalescers/coalescers media, and Sepra-Chem is the Licensor (UOP) recommended supplier. PALL TRINITY MICRO CORP and Sepra-Chem are in the BMP Approved Vendors List. Therefore, TTSJV shall ensure that both PALL TRINITY MICRO CORP and Sepra-Chem are on the vendors list that will receive the MR of both 3HDU Feed Coalescer 021V0001 and Diesel Product Coalescer 021V0012.