## 021-C-GAD-00002-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | Add equipment name
2 | Text Box | 1 | Mahdi Ali | Add Equipment number
3 | Text Box | 1 | Ali Kadhem | Please refer to the comments provided in email: "3HDU - Pre EPC - Comments on some datasheets", dated 3 April 2018: It is noted in FEED datasheet that many dimensions w.r.t. tray spacing are not rounded off to the nearest mm while converting from UOP datasheet; there is a variation of about 5mm in some rounding off. EPCContractor should refer to UOP datasheet for the base dimensions and round off to nearest mm while developing the EPC datasheet.