## 021-C-GAD-00003-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Jawad Alawi | 021C0002
2 | Text Box | 1 | rob.urban | Add equipment name
3 | Text Box | 1 | Mahdi Ali | Add Equipment number
4 | Text Box | 1 | Ali Kadhem | Please refer to the comments provided in email: "3HDU - Pre EPC - Comments on some datasheets", dated 3 April 2018: As per the sketch in the datasheet, the gas entry is shown above the LIT top tap. However, based on the dimensions, the gas entry will be below the top level tap. This issue was raised to UOP during FEED and UOP had confirmed that the dimesions are correct. Bapco has a concern with this arrangement i.e. gas entry being below 100% liquid level reading. Bapco preference is to keep the gas entry point above the upper liquid level tap. UOP's further clarification for the rational of the current arrangement and to advise if they foresee any concern with Bapco's preferred arrangement.