## 021-C-GAD-00019-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Rashed Almudahka | Add "w/ vortex breaker" to N2 notes
2 | Call-out | 1 | Ali Kadhem | As per 021V0017 datasheet (Rev.A Issue For Inquiry): 8"(HOLD). Please check and update.
3 | Call-out | 1 | Rashed Almudahka | Forgings grade shall be LF2 as per FEED. please clarify.
4 | Call-out | 1 | Rashed Almudahka | Provide the basis of selecting A333 specification for internal piping which is known for low temperature services.