## 021-C-GAD-00022-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Rashed Almudahka | show the inlet piping for N14.
2 | Call-out | 1 | Rashed Almudahka | TYPICAL COMMENT TO ALL GADs "A" view is not marked in the sketch. Also, no nozzles are represented in on the plan.
3 | Call-out | 1 | Rashed Almudahka | Vortex breaker is not shown in the PDS. clarify and ensure consistency between the two documents and P&ID.