## 021-C-GAD-00032-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | As per EDP drawing , Note 2: “For temperature and pressure curves see subsheets immediately following this vessel sheet”, i.e. sheets 992381-301-9A/9B/9C. Please check and include.
2 | Text Box | 1 | Mahdi Ali | INCLUDE EQUIPMENT TAG NUMBER IN ALL SHEETS.