## 021-E-DAT-00010-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 4 | Rashed Almudahka | As per shell discharge piping spec. material shall be NACE. JV to clarify
2 | Call-out | 5 | Rashed Almudahka | This is a mechanical data sheet, JV to confirm whether the note has been verified.