## 021-E-DAT-00014-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 3 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
3 | Text Box | 5 | Ali Kadhem | As per Licensor (EDP) datasheet note no.1 "Design for hydrogen service per UOP Standard Specification 4-11, section 4.6 or 4-12, section 3.4 on tube side. Please check and include.