## 021-E-DAT-00016-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Ali Kadhem | The inlet operating pressure as per the EDP datasheet is 216.6psig. Please check and confirm.
3 | Call-out | 3 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
4 | Call-out | 3 | Ali Kadhem | The tube sheet design temperature as per the FEED datasheet is 500F. Please provide rational for this change