## 021-E-DAT-00019-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | COOLERS
2 | Callout | 1 | Mahdi Ali | EQUIPMENT TAG NUMBER SHALL NOT CONTAIN SPACES
3 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
4 | Callout | 1 | Mahdi Ali | UNIT NUMBER SHALL NOT INCLUDE THE AREA CODE
5 | Call-out | 2 | Rashed Almudahka | Note6 referred herein is deleted from the notes sheet. please clarify
6 | Call-out | 3 | Ali Kadhem | It is noted that the tube side design pressure in FEED and EDP datasheets was 165psig. However, in this datasheet it has been changed to 115psig. Please provide rational for this change.
7 | Text Box | 3 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, thickness, pitch and length) mentioned in this datasheet and the Licensor datasheet (EDP). Please provide the rational for those differences.
8 | Call-out | 5 | Rashed Almudahka | Full RT is required for shell side. please modify
9 | Text Box | 6 | Ali Kadhem | As per Licensor (EDP) datasheet note no.1: “Design for wet H2S service per UOP Standard Specification 4-11, section 4.7 or 4-12, section 3.5 on shell side.” Please include.