## 021-G-DAT-00003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | Comments to be discussed
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Call-out | 2 | Ali Kadhem | It is noted that the discharge pressure is revised in comparison with FEED datasheet/IBD P&ID. Please confirm this is based on the EPC latest hydraulic calculation.
4 | Callout | 4 | Isamu | Socket
5 | Text Box | 4 | Isamu | Dual pressurized (plan 53B) shall be provided as per Feed data sheet. Plan 32 is also necessary for impeller side flushing from solid particles. Comply and correct accordingly
6 | Text Box | 5 | Isamu | All inspection and test specified as witnessed on FEED data sheet shall remain witnessed. The use of the term Observed in the data sheet is rejected. Correct accordingly and put a remark as agreed on the definitions of words between API / BMPS and ITP
7 | Call-out | 7 | Mahdi Ali | INCORRECT TAG NUMBER