## 021-G-DAT-00006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | Comments to be discussed
2 | Call-out | 2 | Ali Kadhem | It is noted that the discharge pressure is revised in comparison with FEED/EDP datasheet. Please confirm this is based on the EPC latest hydraulic calculation.
3 | Text Box | 3 | AliRedha Malalla | AVL
4 | Text Box | 3 | AliRedha Malalla | Refer to Approved Vendor List
5 | Text Box | 4 | Isamu | Change to plan 21 or 23. Plan 11 is not suitable for elevated process temperature in the range of this application. See API 682 / Comply and consult with Vendor
6 | Text Box | 4 | AliRedha Malalla | T
7 | Text Box | 4 | AliRedha Malalla | AVL
8 | Text Box | 5 | Isamu | All inspection and test specified as witnessed on FEED data sheet shall remain witnessed. The use of the term Observed in the data sheet is rejected. Correct accordingly and put a remark as agreed on the definitions of words between API / BMPS and ITP
9 | Call-out | 7 | Ali Kadhem | As per BMPS-A1 steam (HPS) condition for “NORMAL” case is 540psig@700F, whereas, 530psig @700F is specified in this datasheet. Our understanding is that 10psi pressure drop has been considered. Please confirm.
10 | Call-out | 7 | Ali Kadhem | As per BMPS-A1 steam (LPS) condition for “MAXIMUM” and “NORMAL” cases are 70psig and 60 psig, however, in this datasheet, 80psig and 70psig were specified. Our understanding is that 10psi for pressure drop has been considered. Please confirm.
11 | Call-out | 7 | Ali Kadhem | Please provide rational for specifying the steam (HPS) condition for the “RATED” case as 485psig @650F and for “MIN” case is 550psig @735F.
12 | Arrow | 7 | Ali Kadhem
13 | Call-out | 7 | Ali Kadhem | Please provide rational for specifying the steam (LPS) condition for the “MIN” case as 70psig.
14 | Text Box | 7 | Ali Kadhem | Please provide the rational for not including the Licensor (EDP) datasheet note no. M10b: "Motor shall have torque capability to accelerate the pump to operating speed with discharge shutoff valve open, and the discharge check valve closed against a static pressure of 135psi(g)."