## 021-G-DAT-00007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | Comments to be discussed
2 | Call-out | 2 | Ali Kadhem | Please specify the value of the NPSH (available).
3 | Call-out | 2 | Ali Kadhem | It is noted that the suction and discharge pressure have revised in comparison with FEED/EDP datasheets. Please confirm that this is based on the EPC latest hydraulic calculation.
4 | Text Box | 4 | Isamu | All seal flush and seal barrier liquid lines shall be SS piping as per FEED data sheet. Contractor is not at liberty to select softer option in case of conflict between various project documents. Correct and apply to all pumps
5 | Text Box | 4 | Isamu | Check with Seal pump maker/seal vendor if impeller side mech seal flushing is covered by plan 53B. Otherwise provide suitable seal flush plan
6 | Text Box | 4 | AliRedha Malalla | NOTE (25)
7 | Text Box | 4 | AliRedha Malalla | T
8 | Text Box | 4 | AliRedha Malalla | AVL
9 | Text Box | 5 | Isamu | All inspection and test specified as witnessed on FEED data sheet shall remain witnessed. The use of the term Observed in the data sheet is rejected. Correct accordingly and put a remark as agreed on the definitions of words between API / BMPS and ITP
10 | Text Box | 7 | AliRedha Malalla | 25. PUMP & M/SEAL OEM SHALL PROVIDE MEASURED STUFFING BOX PRESSURE.
11 | Call-out | 7 | Ali Kadhem | As per BMPS-G2 6.1.8 (for amine services) add a note as follow: "NPSH (required) shall not be more than 55% of NPSH (available). Refer to project specification BMPS-G2 for further information.”