## 021-G-DAT-00008-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Text Box | 1 | Rashed Almudahka | TYPICAL COMMENTS are applicable to all data sheets included in this transmittal.
3 | Call-out | 2 | Rashed Almudahka | It is noted that operating conditions has been changed from FEED. Please confirm this is as per latest hydraulics study
4 | Call-out | 3 | Rashed Almudahka | Material class is S-6 as per FEED data sheet. provide the basis of this change
5 | Call-out | 3 | Rashed Almudahka | Provide the basis of changing the design pressure from 180 to 220psig.
6 | Call-out | 3 | Rashed Almudahka | TYPICAL COMMENT As per FEED, coupling should be in compliance with API610. please clarify
7 | Callout | 4 | Isamu | SS piping
8 | Text Box | 5 | Rashed Almudahka | TYPICAL COMMENT Provide the basis of changing the inspection/ test requirement.
9 | Text Box | 6 | David.Jimenez | please advise