## 021-G-DAT-00008-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ravi Kumar | OPEN COMMENT IN RESOLUTION SHEET OF REV A DATASHEET TO BE CLOSED
2 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
3 | Callout | 2 | Mahdi Ali | 021 - NO. 3 HYDRODESULPHURIZATION UNIT
4 | Call-out | 2 | Ebrahim | Indicate method of starting the motor. Normally, Direct-On-Line (DOL)
5 | Call-out | 4 | Ali Hasan | Dual-pressurized seal (plan 53B) has been specified for this pump and the other pumps in this transmittal (021P0010A/B and 021P0011A/B): 1.Please confirm with the pump vendor and the mechanical seal supplier that dual-pressurized seal can be used for these pumps considering that the pumps are intermittent service, vertical (submerged) and multistage type. 2.Please ensure consistency/standardization in the mechanical seal selection with other pumps of similar in ROC, MOC and SOC.