## 021-G-DAT-00011-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Rashed Almudahka | As per EDP pump note no. 29, minimum flow should not be less than 30gpm. please clarify
3 | Call-out | 2 | Ali Kadhem | Please specify the value of the NPSH(available).
4 | Text Box | 2 | Isamu | Please use dot "." instead of comma "," to avoid confusing and provide uniformity
5 | Text Box | 3 | Isamu | RF is not suitable with #900 rating. Change to RJT
6 | Call-out | 3 | Rashed Almudahka | As per P&ID, piping class of suction and discharge is D2, which is 600# rating as per BMPS-L2. please advise.
7 | Text Box | 3 | Isamu | This oil can not be used with integrally geared OH6. Delete and leave it to Vendor to fill.
8 | Text Box | 3 | Isamu | Diffuser shall be SS material, otherwise pump performance will deteriorate in a month. Check with Vendor
9 | Call-out | 3 | Rashed Almudahka | As per FEED and EDP data sheets, barrel and case material shall be KCS. please modify.
10 | Call-out | 3 | Rashed Almudahka | As per FEED data sheet, coupling should be in compliance with API610. please modify.
11 | Text Box | 4 | Isamu | Plan 13 is for volatile/saturated/low specific gravity liquid and it is totally not suitable here. Indicate plan 11 and consult the Vendor to confirm its suitability
12 | Text Box | 4 | Isamu | Leave this to the Vendor to fill as it is not applicable to integrally geared pump
13 | Text Box | 5 | Rashed Almudahka | provide the basis of changing number of tests from witness (as per FEED data sheet) to observe.
14 | Call-out | 5 | Rashed Almudahka | liquid penetrant is required as per FEED DS. please modify
15 | Call-out | 6 | Rashed Almudahka | provide the basis of removing the remark which stated the following
16 | Callout | 7 | Mahdi Ali | INCORRECT TAG NUMBER
17 | Call-out | 7 | Ali Kadhem | As per BMPS-G2 6.1.8 (for water injection), note no.13 to be modified to: “NPSH (required) shall not be more than 55% of NPSH (available). Refer to project specification BMPS-G2 for further information.”
18 | Text Box | 7 | Ali Kadhem | As per the Licensor (EDP) datasheet the pump type is “Sundyne”, and note no.40 “Supplier (Recommended): Sundyne Corporation”. Please advise how this is planned to be achieved.