## 021-G-DAT-00012-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Text Box | 2 | Mahdi Ali | 021 -
3 | Call-out | 2 | Ali Kadhem | It is noted that the discharge pressure has been revised in comparison with FEED/EDP datasheets. Please confirm that this is based on EPC latest hydraulic calculation.
4 | Text Box | 2 | AliRedha Malalla | Please verify, FEED DS is ASME B73.1
5 | Call-out | 3 | Rashed Almudahka | API type as per FEED and EDP data sheets was OH1. Please provide the basis of the changing it to OH2.
6 | Call-out | 3 | Rashed Almudahka | note no. 20 is deleted. please clarify
7 | Text Box | 3 | Isamu | There is no barrel in OH2 type pumps. Please delete and leave it to Vendor
8 | Call-out | 4 | Rashed Almudahka | Flat surface shall be required as per EDP data sheet. please clarify.
9 | Call-out | 4 | Rashed Almudahka | socket
10 | Call-out | 5 | Rashed Almudahka | Confirm the inspection required is as per BMPS-G3
11 | Text Box | 5 | Rashed Almudahka | Provide the basis of changing all tests from witness as per FEED data sheet to observe.
12 | Text Box | 7 | Ali Kadhem | As per BMPS-G2 6.1.8, please add the following note: “NPSH available should exceed NPSH required by at least 1.3 m (4 ft). Refer to project specification BMPS-G2 for further information”. Otherwise please provide rational for not including this note.