## 021-L-INX-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Why the cover sheet is A3 size and the rest of the spreadsheet is A4 size? Use the correct cover sheet size. The latest templates include the correct cover sheets.
2 | Call-out | 2 | Hasan Al Noaimi | future
3 | Call-out | 2 | Ali Kadhem | Diesel to storage flowrate is different than flowrate mentioned for design/operating cases of IBD PFD. Please check and confirm/revise.
4 | Call-out | 2 | Ali Kadhem | 136oF. As per IBD PFD. Please check and confirm.
5 | Call-out | 2 | Ali Kadhem | 52.0 lb/ft3. As per IBD PFD. Please check and confirm.
6 | Call-out | 2 | Ali Kadhem | 135oF. As per IBD PFD. Please check and confirm.
7 | Call-out | 2 | Ali Kadhem | TTSJV to confirm that this line is designed to route both wild naphtha from 021V0010 and ejector receiver oil from 021V0013.
8 | Callout | 2 | Robert.Kawitzki | Add 3 off columns for northing, easting and EL
9 | Callout | 2 | Robert.Kawitzki | Add column for insulation thickness
10 | Call-out | 2 | Hasan Al Noaimi | delete
11 | Call-out | 2 | Ali Kadhem | 1.80cP. As per IBD PFD. Please check and confirm.
12 | Call-out | 3 | Rashed Almudahka | As per BMPS-N1 and service normal temperature, Ipp insulation is not required.
13 | Call-out | 3 | Ali Kadhem | With reference to FEED utility consumption summary sheet, 110 psig steam export is 10,654 lb/hr. Please check and confirm.
14 | Call-out | 3 | Rashed Almudahka | As per BMPS-N1 and service normal temperature, at least Ipp insulation shall be provided.
15 | Call-out | 3 | Ali Kadhem | With reference to FEED utility consumption summary sheet, 550 psig steam consumption is 84,780 lb/hr. Please check and confirm.
16 | Call-out | 3 | Ali Kadhem | With reference to FEED utility consumption summary sheet, 60 psig steam export is 90,254 lb/hr. Please check and confirm.
17 | Call-out | 3 | Ali Kadhem | Rich and lean amine flowrates are different than flowrates mentioned for design/operating cases of IBD PFD. Please check and confirm/revise.
18 | Call-out | 4 | Hasan Al Noaimi | No 1 N2 Plant
19 | Call-out | 4 | Ali Kadhem | With reference to FEED utility consumption summary sheet, BFW (LP) consumption is 5774 lb/hr. Please check and confirm.
20 | Call-out | 4 | Hasan Al Noaimi | CWT
21 | Call-out | 5 | Hasan Al Noaimi | from H2 Header
22 | Call-out | 5 | Hasan Al Noaimi | CWT