## 021-P-INX-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Mahdi Ali | EQUIPMENT TAGS SHALL NOT CONTAIN SPACES
2 | Call-out | 5 | Ali Kadhem | As per the Backwash Surge Drum 021V0018 FEED datasheet, the normal operating pressure is 10 psig and the design pressure (internal) is 75 psig. Please clarify/revise.
3 | Call-out | 5 | Ali Kadhem | As per the Feed Coalescer 021V0001 FEED datasheet, the operating pressure is 100.95 psig. Please clarify/revise.
4 | Call-out | 5 | Ali Kadhem | As per the Feed Filter 021U0001 datasheet issued by TTSJV, the feed temperature considered to be in the range of 130 to 160oF. Please clarify/revise.
5 | Call-out | 5 | Ali Kadhem | As per the Feed Filter 021U0001 datasheet issued by TTSJV, the operating pressure is 121psig. Please clarify/revise.
6 | Call-out | 7 | Ali Kadhem | As per 021P0001A/B datasheet issued by TTSJV, the discharge pressure is 1334.3psig. Please confirm/revise.
7 | Call-out | 7 | Ali Kadhem | As per 021P0003A/B datasheet issued by TTSJV, the discharge pressure is 219psig. Please confirm/revise.
8 | Call-out | 7 | Ali Kadhem | As per 021P0005A/B datasheet issued by TTSJV, the discharge pressure is 128.6psig. Please confirm/revise.
9 | Call-out | 7 | Ali Kadhem | As per 021P0008A/B datasheet issued by TTSJV, the discharge pressure is 132.7psig. Please confirm/revise.
10 | Call-out | 7 | Ali Kadhem | As per the Backwash Pumps 021P0008A/B datasheet issued by TTSJV, the normal operating temperature is 130oF and the maximum temperature is 160oF. Please clarify/revise.
11 | Call-out | 7 | Ali Kadhem | It is noted that for the other pumps, the discharge pressure was specified, however, for this pump the suction pressure was considered. Please clarify/revise.
12 | Call-out | 8 | Ali Kadhem | It is noted that for the other pumps, the discharge condition (temperature/pressure) were specified, however, for those pumps the suction condition was considered. Please clarify/revise.