## 022-A-PID-00001-020-R9A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION
2 | Callout | 1 | Mahdi Ali | THE DRAWING REVISION PROVIDED BY BAPCO WAS REV. '11'. THUS THIS DRAWING SHOULD HOLD REVISION '11A'.
3 | Call-out | 1 | Edgardo | Please change to 7CDU
4 | Text Box | 1 | A Albalooshi | General comment: Comments raised in the joint P&ID meeting with TechnipFMC shall be incorporated in the P&ID. Meeting held with TechnipFMC on 18 July 2018.
5 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS