## 023-A-PID-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest P&ID border.
2 | Call-out | 1 | MAK | Retain the font style, font height and text positions of the entire title block and the entire border.
3 | Call-out | 1 | Mahdi Ali | Remove short description. Short description can be added only of there is not enough space for the long description
4 | Text Box | 1 | rob.urban | THESE MINOR COMMENTS ARE IN ADDITION TO MARK UPS DONE DURING THE JOINT P7ID REVIEW
5 | Text Box | 1 | Mahdi Ali | Motor tag shall be shown
6 | Text Box | 1 | Mahdi Ali | Where the details are shown?
7 | Text Box | 1 | Ahmed Habib | 2oo3
8 | Text Box | 1 | Mahdi Ali | General Notes and Notes shall be combined. All notes shall be numbered.
9 | Text Box | 1 | Mahdi Ali | descriptions in the Title shall be equally spaced.
10 | Text Box | 1 | Mahdi Ali | Values to be right justified for all equipment attributes
11 | Callout | 1 | Salman Jaffer | Provide PI readable from PV0003 bypass
12 | Text Box | 1 | Mahdi Ali | Size of the valves to be shown
13 | Call-out | 1 | MAK | Change to NTS
14 | Text Box | 1 | Mahdi Ali | Show Arrow
15 | Call-out | 1 | Hasan Al Noaimi | as per spec should be 3/4 not 1 inch
16 | Text Box | 1 | AliRedha Malalla | Symbol to be corrected, without 'dot'. Discrepancy between suction flanges of 023P0001A & B.