## 023-A-STS-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
2 | Call-out | 2 | Rashed Almudahka | JV to revise and confirm this value
3 | Typewritten Text | 2 | steven.coyne | Add Reference to Procedure , Criticality Assessment 000-A-PRO-50017-001
4 | Call-out | 2 | Rashed Almudahka | JV to revise and confirm this value
5 | Call-out | 2 | Ebrahim | Motors are not listed?!
6 | Call-out | 2 | Ebrahim | Criticality Rating to be defined
7 | Call-out | 2 | Ebrahim | Bases of the given values need to be defined or shall be referenced to a document
8 | Call-out | 2 | Rashed Almudahka | JV to revise and confirm this value
9 | Call-out | 2 | Rashed Almudahka | JV to revise and confirm these values
10 | Call-out | 2 | Ebrahim | Do not use short form of description. Typical